## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design | Initial Architecture/Database Setup & Design | Web Portal Redesign | Develop iOS Compatible Mobile App | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
Develop iOS Compatible Mobile App | Manual Importing | Upgrade Database | Develop Android Compatible Mobile App | Mobile App User Interface Refinement
Develop Android Compatible Mobile App | Develop Web Portal application | Security Update |  | Automated Amber Alerts
Develop Web Portal application | Basic Data Searching Capability | User Based Preferences- Save Search & Reports |  | Send Manual Amber Alerts by Region
Upgrade Database | Authentication- Login/Logout |  |  | Automated Integration for Importing
Security Update | Basic Dashboard with heatmap display |  |  | In-App messaging for Doctors and Patients
Manual Importing | Web Report of Data (View only no Export) |  |  | Export CSV of Reported Data
Automated Integration for Importing
Mobile App User Interface Refinement
Authentication- Login/Logout
Basic Dashboard with heatmap display
Basic Data Searching Capability
Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports
Web Portal Redesign
Export CSV of Reported Data
Send Manual Amber Alerts by Region
Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | so that I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | that I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company
Doctor | add the name of patients I have treated | I can add treatments | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional
Doctor | login to the system | I can enter patient treatment information | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered
Healthcare Company | reset my password by myself | that I can login again. | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page
Test Center | update/change the number of test kits received | data is accurate | As a Test Center I can update/change the number of test kits received so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page
Test Center | be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low
CDC Official | view the number of virus test kits administered by the test centers | I am able to monitor the test kits number in different test centers | As a CDC Official I can view the number of virus test kits administered by the test centers so that I am able to monitor the test kits number in different test centers. | 1.User can check the stock of the kits 2.The number of kits is real-time updated
CDC Official | download the virus status report | I can use the paper report to do analysis | As a CDC Official I can download the virus status report so that I can use the paper report to do analysis. | 1.User can download the report 2.User can customize the contents in the report 3.User can drag the graphs or texts in the report 4.User can show/hide graphs
Doctor | delete the name of people who return health | the patients data is more accurate | As a Doctor I can delete the name of people who return health so that the patients data is more accurate. | 1.User can change the patients status to RECOVERED 2.Alpha Numeric characters are allowed 3.Patients recovery data is required
Doctor | write report | I am be able to report successful remedies and cures for patients that have contracted the virus | As a Doctor I can write report so that I am be able to report successful remedies and cures for patients that have contracted the virus. | 1.User can write text 2.User can edit text 3.User can (temporaty) save text 4.User can delete text 5. Alpha Numeric characters are allowed
Healthcare Company | see where test kits have been sent to | I can recall the nonconforming products | As a Healthcare Company I can see where test kits have been sent to so that I can recall the nonconforming products. | 1.User can see the data of different batch of test kits that have been sent out 2.User can see where the test kits have sent to
Healthcare Company | see the number of kits have been used in different centers | I can track wheather each kit is used. | As a Healthcare Company I can see the number of kits have been used in different centers so that I can track wheather each kit is used.. | 1.User can see the number of kits in each batch that have been used 2.User can see the number of kits in each batch that have not been used 3.User can filter the result by State
Medical Examiner | records deadth caused by the virus | the death toll is updated everyday | As a Medical Examiner I can records deadth caused by the virus so that the death toll is updated everyday. | 1.Only numeric characters allowed 2.User must verify and confirm before updating the death toll 3.the history records and operations will be logged
Medical Examiner | tell the death's contact person that he/she passed away | the death's contact person will be notified | As a Medical Examiner I can tell the death's contact person that he/she passed away so that the death's contact person will be notified. | 1.User only need to click a button 2.User cannot click this button, if the patient was not declared dead
Patient | download the app on an Android phone | I can use the app | As a Patient I can download the app on an Android phone so that I can use the app. | 1.User can find the app on Google Market 2.User can download it freely
Patient | login to the app | I can check the latest status of the spreading of the virus | As a Patient I can login to the app so that I can check the latest status of the spreading of the virus. | 1.User need login in the first time 2.User name (or phone number) and password are required 3.User will receive a password reset email/voice message after 3 incorrect entries 4.User will login automatically after the first login
System Administrator | hide some data | hide some sensitive data | As a System Administrator I can hide some data so that hide some sensitive data. | 1.User can manually modify total death toll 2.Only numeric characters allowed
System Administrator | hide some data | hide some error data | As a System Administrator I can hide some data so that hide some error data. | 1.Alpha Numeric characters are allowed 2.User can manually hide error data
System Administrator | check the log | check if there is any misoperation | As a System Administrator I can check the log so that check if there is any misoperation. | 1.the operation history will be logged automatically 2.User can review the log 3.User cannot change the log
Test Center | check the logistic status of the kits that is on the way to the Test Center | I know where it is | As a Test Center I can check the logistic status of the kits that is on the way to the Test Center so that I know where it is. | 1.User must login 2.User can only view the logistic status
Test Center | notify patients/doctors if there is not enough test kits | people do not have to come | As a Test Center I can notify patients/doctors if there is not enough test kits so that people do not have to come. | 1. The color of the Test Center on the system will be gray 2. The Test Center cannot be selected
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) - Release 1 (MVP) contains 3 sprints. The release can only have 10 user stories within the 3 sprints - Sprint 1 will have 3 user stories - Sprint 2 will have 4 user stories - Sprint 3 will have 3 user stories - Release 2 contains 2 sprints. The release can only have 10 user stories within the 2 sprints - Sprint 4 and Sprint 5 will each have 5 user stories - Release 3 contains 2 sprints. The release can only have 5 user stories within the 2 sprints - Sprint 6 will have 2 user stories - Sprint 7 will have 3 user stories - All remaining user stories are assigned to "Backlog for Future Release" - Assign the sprint that the user stories will be in within that particular release in Column E. If it is is "Backlog for Future Release" the user story doesn't need to be assigned a sprint. |  |  |  |  | Hints/Tips: - Question if a user role has too much functionality to be in the MVP release. - Question what is a nice-to-have vs high-value based on the scenario and vision. - Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. - Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Release | Sprint | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view | Release 1 (MVP) | 2 | 1 Total Stories = 3 | 3
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company | Release 1 (MVP) | 3 | 2 Total Stories = 4 | 4
Doctor | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional | Release 1 (MVP) | 1 | 3 Total Stories = 3 | 3
Doctor | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries | Release 1 (MVP) | 1 | 4 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered | Release 1 (MVP) | 2 | 5 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password | Release 1 (MVP) | 3 | 6 Total Stories = 2 |  |  | 2
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials | Release 2 | 4 | 7 Total Stories = 3 |  |  | 3
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page | Release 1 (MVP) | 3 | Sum | 10 | 10 | 5
Patient | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results | Release 2 | 5 | Total | 10 | 10 | 5 | 4
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state | Release 2 | 5 | SUM = TOTAL | #NAME? | #NAME? | #NAME?
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access | Release 1 (MVP) | 1
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page | Release 2 | 4
Test Center | As a Test Center I can update/change the number of test kits received so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page | Release 1 (MVP) | 2
Test Center | As a Test Center I can be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low | Backlog for Future Release | 0
CDC Official | As a CDC Official I can view the number of virus test kits administered by the test centers so that I am able to monitor the test kits number in different test centers. | 1.User can check the stock of the kits 2.The number of kits is real-time updated | Release 2 | 5
CDC Official | As a CDC Official I can download the virus status report so that I can use the paper report to do analysis. | 1.User can download the report 2.User can customize the contents in the report 3.User can drag the graphs or texts in the report 4.User can show/hide graphs | Release 2 | 5
Doctor | As a Doctor I can delete the name of people who return health so that the patients data is more accurate. | 1.User can change the patients status to RECOVERED 2.Alpha Numeric characters are allowed 3.Patients recovery data is required | Release 1 (MVP) | 2
Doctor | As a Doctor I can write report so that I am be able to report successful remedies and cures for patients that have contracted the virus. | 1.User can write text 2.User can edit text 3.User can (temporaty) save text 4.User can delete text 5. Alpha Numeric characters are allowed | Release 2 | 4
Healthcare Company | As a Healthcare Company I can see where test kits have been sent to so that I can recall the nonconforming products. | 1.User can see the data of different batch of test kits that have been sent out 2.User can see where the test kits have sent to | Backlog for Future Release | 0
Healthcare Company | As a Healthcare Company I can see the number of kits have been used in different centers so that I can track wheather each kit is used.. | 1.User can see the number of kits in each batch that have been used 2.User can see the number of kits in each batch that have not been used 3.User can filter the result by State | Release 3 | 7
Medical Examiner | As a Medical Examiner I can records deadth caused by the virus so that the death toll is updated everyday. | 1.Only numeric characters allowed 2.User must verify and confirm before updating the death toll 3.the history records and operations will be logged | Release 2 | 4
Medical Examiner | As a Medical Examiner I can tell the death's contact person that he/she passed away so that the death's contact person will be notified. | 1.User only need to click a button 2.User cannot click this button, if the patient was not declared dead | Backlog for Future Release | 0
Patient | As a Patient I can download the app on an Android phone so that I can use the app. | 1.User can find the app on Google Market 2.User can download it freely | Release 3 | 6
Patient | As a Patient I can login to the app so that I can check the latest status of the spreading of the virus. | 1.User need login in the first time 2.User name (or phone number) and password are required 3.User will receive a password reset email/voice message after 3 incorrect entries 4.User will login automatically after the first login | Release 3 | 6
System Administrator | As a System Administrator I can hide some data so that hide some sensitive data. | 1.User can manually modify total death toll 2.Only numeric characters allowed | Release 3 | 7
System Administrator | As a System Administrator I can hide some data so that hide some error data. | 1.Alpha Numeric characters are allowed 2.User can manually hide error data | Release 3 | 7
System Administrator | As a System Administrator I can check the log so that check if there is any misoperation. | 1.the operation history will be logged automatically 2.User can review the log 3.User cannot change the log | Release 2 | 4
Test Center | As a Test Center I can check the logistic status of the kits that is on the way to the Test Center so that I know where it is. | 1.User must login 2.User can only view the logistic status | Backlog for Future Release | 0
Test Center | As a Test Center I can notify patients/doctors if there is not enough test kits so that people do not have to come. | 1. The color of the Test Center on the system will be gray 2. The Test Center cannot be selected | Release 2 | 5
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1 (MVP) user stories from Priority sheet into column C, Rows 3-12 below in the appropriate sprint. Copy your 10 Release 2 user stories from Priority sheet into column C, Rows 13-22 below in the appropriate sprint. Copy your 5 Release 3 user stories from Priority sheet into column C, Rows 23-27 below in the appropriate sprint.
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 | As a System Administrator I can give access to the system so that users can access,import, share data.. | 5
|  | As a Doctor I can login to the system so that I can enter patient treatment information. | 1
|  | As a Doctor I can add the name of patients I have treated so that I can add treatments . | 1
| Sprint 2 | As a Doctor I can delete the name of people who return health so that the patients data is more accurate. | 1
|  | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | 3
|  | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | 3
|  | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | 2
| Sprint 3 | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | 3
|  | As a Healthcare Company I can reset my password by myself so that that I can login again. . | 2
|  | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | 1
Release 2 | Sprint 4 | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 0.5
|  | As a System Administrator I can remove access so that users are not able to access the system. | 1
|  | As a System Administrator I can check the log so that check if there is any misoperation. | 3
|  | As a Medical Examiner I can records deadth caused by the virus so that the death toll is updated everyday. | 1
|  | As a Doctor I can write report so that I am be able to report successful remedies and cures for patients that have contracted the virus. | 2
| Sprint 5 | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | 1
|  | As a Test Center I can notify patients/doctors if there is not enough test kits so that people do not have to come. | 2
|  | As a Patient I can change my test results so that the system data is accurate. | 1
|  | As a CDC Official I can view the number of virus test kits administered by the test centers so that I am able to monitor the test kits number in different test centers. | 1
|  | As a CDC Official I can download the virus status report so that I can use the paper report to do analysis. | 2
Release 3 | Sprint 6 | As a Patient I can download the app on an Android phone so that I can use the app. | 5
|  | As a Patient I can login to the app so that I can check the latest status of the spreading of the virus. | 3
| Sprint 7 | As a Healthcare Company I can see the number of kits have been used in different centers so that I can track wheather each kit is used.. | 3
|  | As a System Administrator I can hide some data so that hide some sensitive data. | 1
|  | As a System Administrator I can hide some data so that hide some error data. | 1